## Sheet1
PROJECT BACKLOG
9 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 自习室推荐 | 作为一名考研学生，我希望可以有自习室推荐功能 | Initial Feature | Not Done | 3 | 90 |  |  | 2
2 | 1 | 1 | user story | 自习室记录 | 作为一名考研学生，我希望我选择的自习室有历史记录功能 | Initial Feature | Not Done | 3 | 95 |  |  | 2
3 | 1 | 1 | user story | 根据条件筛选 | 作为一名考研学生，我希望能有自己的个人喜欢的条件来选择自习室 | Initial Feature | Not Done | 3 | 80 |  |  | 2
4 | 1 | 1 | user story | 自习室筛选 | 作为一名考研学生，我希望通过距离，好评，销量等条件来筛选自习室 | Initial Feature | Not Done | 4 | 85 |  |  | 2
5 | 1 | 1 | user story | 自习室评价 | 作为一名考研学生，我希望能给选择的自习室评价，以便其他人选择优质自习室 | Initial Feature | Not Done | 2 | 85 |  |  | 1
6 | 1 | 1 | user story | 自习室分享 | 作为一名使用过的学生，我希望能将自己的意见建议和使用经历分享给其他工作人，提供给他们帮助减少他们的困扰。 | Initial Feature | Not Done | 1 | 80 |  |  | 1
7 | 1 | 1 | user story | 自习室位置共享和定位 | 作为一名考研学生，我希望能在APP上进行定位并了解我去自习室的路线和最优推荐，以便快捷解决问题。 | Initial Feature | Not Done | 1 | 85 |  |  | 1
8 | 1 | 1 | user story | 登录方式 | 作为一个注册用户，我希望采取便捷的微信和QQ微博关联授权直接登录，以便于我更方便快捷的登陆。 | Initial Feature | Not Done | 3 | 60 |  |  | 2 | #REF!
9 | 1 | 1 | user story | 支付方式 | 作为一名消费者，我希望采取支付宝和微信或者手机银行支付方式，以便快速支付 | Initial Feature | Not Done | 4 | 60 |  |  | 2
10 | 1 | 1 | user story | 自习室搜索 | 作为一名考研学生，我希望可以通过名称等进行自习室的搜索 | Initial Feature | Not Done | 2 | 70 |  |  | 1
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information